CMPE314 – SOFTWARE ENGINEERING
Lab 2 Solution: Resource Allocation and Project Planning

Project: FitTrack – Personal Fitness Companion

Group 3/1: Tawfig Malik (22115813), Lahsen Aittjiou (22118897), Hassan Eihab HassanAli (22211935)

# Part 1 – Resource allocation for sample Gantt

| ID | Task | Resource(s) |
| --- | --- | --- |
| 1 | Requirements Gathering | Alex |
| 2 | Use Case Analysis | Alex/Jamie |
| 3 | System Architecture Design | Jamie |
| 4 | Database Design | Jamie |
| 5 | UI/UX Prototyping | Taylor |
| 6 | Setup Development Environment | Casey |
| 7 | Frontend Development | Taylor |
| 8 | Backend Development | Jamie |
| 9 | API Integration | Jamie/Taylor |
| 10 | Testing (Unit + Integration) | Morgan |
| 11 | User Acceptance Testing | Morgan |
| 12 | Bug Fixing | Jamie/Taylor |
| 13 | Deployment Preparation | Casey |
| 14 | Final Deployment | Casey |
| 15 | Project Documentation | Alex/Casey |

## Allocation explanation

Tasks were assigned according to role: Alex manages requirements and planning, Jamie handles backend, database and architecture, Taylor handles UI/frontend, Morgan handles testing, and Casey handles environment, deployment, and documentation support.

# Part 2 – FitTrack term project plan

| ID | Task | Duration | Dependencies | Assigned member |
| --- | --- | --- | --- | --- |
| P1 | Requirements elicitation | 10 | - | All |
| P2 | UML modeling and DFDs | 10 | P1 | Hassan |
| P3 | UI/UX and HTML/CSS | 10 | P1 | Tawfig |
| P4 | JavaScript/localStorage logic | 12 | P2,P3 | Lahsen |
| P5 | Charts and validation | 5 | P4 | Lahsen |
| P6 | Testing and bug fixes | 10 | P5 | Lahsen/Hassan |
| P7 | Final documentation | 8 | P2,P6 | Hassan |